## Instructions
FlightPro Manager — Master Plan Tracker
Purpose: one place to see everything completed, everything pending verification, everything deliberately on hold, and every not-yet-started feature — so the next piece of work can be picked with the full picture in view, not just whatever's top of mind.
How this workbook is organized:
• Completed — shipped and delivered to the real machine; the great majority is now committed, pushed, and merged into production — see the handoff doc for each item's exact git state.
• Pending — code is done and live, but not yet functionally verified. As of 2026-09-10 there is ONE Urgent row (accessibility, live on production untested since session 7) plus two High compliance GATES that are decisions rather than builds.
• On Hold — explicitly deferred judgment calls and lower-priority findings. Nobody is actively working these; they're parked on purpose, not forgotten.
• New Features (Backlog) — real candidates for what to build next. Each has an Impact and Effort rating and a short rationale to help compare them side by side.
• Summary — counts per sheet and a suggested next-step ordering.
Suggested reading order for a 'what's next' conversation: check Pending first (two Urgent rows are live-on-production-untested and should happen before any new feature work), then compare the New Features sheet's Impact/Effort columns to pick the next build.
Source: compiled from the project's handoff docs (the authoritative running log). Originally built 2026-08-27 from claude/handoff-2026-08-27.md; UPDATED 2026-09-10, backfilling everything from 2026-08-28 onward from claude/handoff-2026-09-03.md and claude/handoff-2026-09-05.md. If this workbook and the newest handoff-*.md ever disagree, THE HANDOFF DOC WINS — it is written as work happens; this is a periodic rollup.

## Completed
# | Area | Item | Details | Date
1 | Security | Admin Setup config-CRUD hardening | Generic whitelisted route (/api/admin/config/[table]) replaces direct client-side Supabase writes for Exercises, Training Programs, Instructor Roles, Sortie Types, Ground School Subjects, Requirement Templates, Holidays. | 2026-08-24 (session 7)
2 | Security | Aircraft Setup hardening | Switched to the existing secured /api/aircraft route instead of direct Supabase writes. | 2026-08-24 (session 7)
3 | Security | IDOR fix — Ground School Progress page | Student login can no longer view another student's progress/DGCA data via the ?student= URL parameter. | 2026-08-24 (session 7)
4 | Security | Forged exam records fix | Direct Exam Entry now goes through a new server-side role-checked route instead of a client-side insert. | 2026-08-24 (session 7)
5 | Accessibility | Escape-to-close on all modals | Shared useEscapeToClose hook wired into all 15 custom modals. | 2026-08-24 (session 7)
6 | Accessibility | aria-label on Close buttons | 11 icon-only Close (X) buttons now have an accessible name. | 2026-08-24 (session 7)
7 | Feature | Breath Analyser (BA) Test Register | New table + secured API routes + data-entry page; Safety Officer role added; SPL/CPL license numbers captured for students/instructors. | 2026-08-19/20
8 | Feature | Breath Analysis Report page | Separate Daily/Weekly/Monthly reporting view with PDF + Excel/CSV export, reusing the register's data. | 2026-08-20 (session 4)
9 | Feature | SPL/CPL Number required-on-completion | Student Pilot License / CPL number now required (client + server) before the SPL requirement can be completed or an instructor created. | 2026-08-19/20
10 | Feature | SPL/CPL Expiry Date fields | Nullable expiry-date columns + form fields for students (SPL) and instructors (CPL). | 2026-08-20
11 | Feature | SPL/CPL Issue Date + auto-expiry | Issue date field added; Expiry Date auto-calculates as Issue Date + 10 years until manually touched. | 2026-08-20/21
12 | Feature | SPL/CPL expiry alerts | Color-coded UI badges on Student/Instructor cards + email notification via the existing cron job, mirroring the medical-expiry pattern. | 2026-08-21 (session 6)
13 | Feature | User Management Edit action | Admins can now edit an existing user's name/email/role, with a self-demotion guard and duplicate-email handling. | 2026-08-20
14 | Feature | Persistent sidebar navigation | Role-filtered left sidebar added across the whole app dashboard shell. | 2026-08-17
15 | Bug fix | Sidebar nav-highlight bug | Instructors vs My Students no longer both highlight due to a string-prefix match bug. | 2026-08-20 (session 2)
16 | Quality | Safe-batch lint cleanup | 166 → 94 lint problems cleared via zero-risk mechanical fixes across 29 files. | 2026-08-20
17 | Security | Solo Release server-side hardening | Requirements Checklist toggle now has a real server-side role check instead of client-trusted only. | 2026-08-19
18 | Quality | Hardcoded-data audit & cleanup | Dead mock-data module removed; several hardcoded lists migrated to DB-driven sources. | 2026-08-19
19 | Feature | Per-phase training-program matching | matchTrainingProgram() resolves a student's stage to the correct training_programs row. | 2026-08-19
20 | Feature | DGCA roll number + real exam score capture | All three ground-school exam entry points now capture the real DGCA roll number and score. | 2026-08-19
21 | Feature | CPL Multi Engine + Simulator hours | Added hour-tracking columns + aircraft type/model data-model restructure to support auto-tracking. | 2026-08-19
22 | Docs | DGCA draft templates (Maintenance Log + Incident Report) | Two draft Word templates built from standard CAR/ICAO conventions — still need user verification against real DGCA forms before implementation. | 2026-08-24
23 | Docs | Pre-Handover Test Plan (Excel) | 36-case P0/P1/P2 test plan covering everything unverified from sessions 2-7, delivered to docs/. | 2026-08-25
24 | Governance | next-steps-plan-2026-08-11.md reconstructed | Accidentally-overwritten project doc rebuilt from cross-referenced sources; marked explicitly as a reconstruction. | 2026-08-25
25 | Permissions | IR required_hours corrected | User confirmed the real DGCA value is 15 (was 40) and fixed it themselves via the now-secured Admin Setup route. | 2026-08-25
26 | Permissions | Instructor roster view access | Instructors can now view (not edit) the full Instructors roster, previously admin/operations-only. | 2026-08-25
27 | Permissions | My Students tab scoped to instructor role | Removed admin/super_admin from this personalized view — they already have the full roster elsewhere. | 2026-08-25
28 | UI cleanup | Dashboard Quick Actions tile grid removed | Redundant now that the persistent sidebar covers the same navigation. | 2026-08-25
29 | Release | All work through 2026-08-25 committed, pushed, and merged into production | main and production both at commit 4aefc5c, confirmed via real terminal output. | 2026-08-25
30 | Bug fix | Medical Expiry null-input console error | React "value prop on input should not be null" — fixed missing ¦¦ '' fallback in lib/store.ts's row mapper and StudentFormModal.tsx's populate-on-edit effect. | 2026-08-26
31 | Accessibility | Broader icon-button aria-label coverage (item 38) | 11 files, 19 buttons — Edit/Delete pencil/trash icons across Admin Setup's 7 CRUD tabs plus Availability/Maintenance/Ground School Attendance pages now labeled with the row's own identifying name, not a generic "Edit"/"Delete". Closes the item deliberately deferred from session 7. | 2026-08-25
32 | Feature | Partial Weekly Off Day scheduling | New FTO Settings option covering all 3 real-world patterns: 1 weekly off, 2 weekly offs, or 1 weekly off + occurrence-based (e.g. every 2nd & 4th Saturday, or every 1st/3rd/5th Saturday). Single shared getSchedulingBlockReason() used by every scheduling surface (BookingForm, ScheduleBoard, GroundSchoolCalendar, store). | 2026-08-25
33 | Bug fix | Partial Weekly Off Day — Settings save not refreshing shared store | Root cause: SettingsTab.tsx wrote settings to Supabase but never refreshed the Zustand store's cached ftoSettings — a pre-existing architectural gap affecting ANY setting change, not just the new feature. Found via user testing (29-08-2026 not blocked), fixed by refreshing the store after save. | 2026-08-25
34 | Security | BA Test Register write access narrowed | Removed admin/super_admin from BA_TEST_WRITE_ROLES — only safety_officer + operations can add/edit entries now; admin/super_admin retain view-only access via the existing REPORTS_VIEW_ROLES. Single source of truth (lib/permissions.ts) closes the gap across the UI and all 3 server routes at once. | 2026-08-26
35 | Feature | Aircraft Maintenance Schedule — Phase 1 | New per-model recurring maintenance schedule (engine TBO, Oil Change, 50/100-Hour Inspection, Annual Inspection, Propeller Service, Avionics Check, AD Compliance/ARC review — DGCA-researched, all 5 fleet models) driving: an Aircraft Model dropdown (with "Other" fallback), a non-blocking "Maintenance Due" warning panel, and staff-confirmed Set-Baseline / Create-Maintenance-Record actions. 4 SQL migrations + 13 code files. Phase 2 (hard-blocking bookings on overdue items) deliberately deferred to backlog. | 2026-08-26
36 | Feature | Aircraft Maintenance Schedule — Type/Model engine-type filtering | Model dropdown now filtered by the selected engine Type (Single/Multi Engine); switching Type clears a now-mismatched Model. A model not yet mapped is shown for either Type so nothing becomes unselectable by omission. | 2026-08-27
37 | Feature | Aircraft Maintenance Schedule — fleet expansion to 9 models | Added Cessna 152, Piper PA-28 Cherokee/Archer, Piper Archer DX, and Diamond DA40 with DGCA/manufacturer-researched schedule data (real sources, same discipline as the original 5 models). | 2026-08-27
38 | Quality | Type/Model engine-type mapping moved from hardcoded to DB-driven | New engine_type column on the schedule-template table, with an Admin Setup selector; adding or changing a model's engine type no longer needs a code change/redeploy — closes the last hardcoded-list gap in this feature. | 2026-08-27
39 | Release | Aircraft Maintenance Schedule Phase 1 + fleet expansion committed, pushed, and merged into production | Two commits (b1a5bd8, 819baef), both independently verified against GitHub. Merged to production before all testing was complete, per the user's explicit informed call. | 2026-08-27
40 | UX / Data integrity | Aircraft Model "Other (custom)" now warns and blocks Save instead of accepting free text | User's own suggestion: a custom Model that doesn't match a schedule template silently broke Maintenance Due tracking (the exact bug found earlier). Picking "Other" in both AircraftFormModal.tsx and AircraftSetupTab.tsx now shows an inline warning naming the current value (if any) and disables Save, pointing the admin at Admin Setup > Aircraft Maintenance Schedule; a "Refresh list" button lets them pick the newly-added model without closing the form. Free text is kept ONLY as a bootstrap fallback for the (currently hypothetical) case of an empty schedule-template table. tsc clean, eslint introduces zero new issues (verified against the pre-edit baseline). Committed, pushed, and merged into production same day (commit e137913) — independently verified via git ls-remote: both main and production resolve to e1379130022e31a028f0d83ae4a6623c9f86d424. | 2026-08-27
41 | Feature | Aircraft Maintenance Schedule — CSV bulk import (Download Template / Upload CSV) | User's request: adding schedule items one at a time was too slow for onboarding a new aircraft type's whole schedule. Added a Download Template / Upload CSV pair to the Admin Setup tab, mirroring ExercisesTab.tsx's existing CSV pattern (same papaparse library, same Append + skip-duplicates rule, no new dependency). Reuses the existing secured bulk-insert path in /api/admin/config/[table]/route.ts (already supported an array body) — no API changes needed. CSV rows can span multiple aircraft models in one upload, not just the currently-selected one. Client-side validates interval_type, interval_value, and engine_type before submitting (the DB CHECK constraints would otherwise fail the WHOLE batch on one bad row, since it's a single insert call) and pre-dedupes against the table's own unique(aircraft_model, item_name) constraint. tsc clean; eslint confirmed zero new issues via before/after diff against the unedited baseline. Committed, pushed, and merged into production same day (commit e137913) — independently verified via git ls-remote: both main and production resolve to e1379130022e31a028f0d83ae4a6623c9f86d424. | 2026-08-27
42 | Security | Test security-hardening round (automated portion) | 2026-08-21 security-hardening round (Admin Setup config-CRUD, Aircraft routes, Direct Exam Entry role gating) verified against LIVE PRODUCTION on 2026-08-28 via an automated Node.js script (scripts/security-hardening-test.mjs) covering all 7 test accounts (super_admin/admin/operations/maintenance/instructor/safety_officer/student): 114/114 automated checks passed, 0 failed. Every non-super_admin role correctly rejected (403) on all 8 Admin Setup config tables (POST tested per table; PATCH/DELETE role gating spot-checked on exercises as the representative table, since every table shares the identical one-line requireRole() check); a non-whitelisted body field was confirmed dropped rather than persisted. Aircraft routes correctly allow only admin/super_admin and reject every other role on POST/PATCH/DELETE. Direct Exam Entry correctly rejects every non-admin/instructor/super_admin role. All throwaway test rows self-cleaned with zero leftovers. Full report: scripts/security-test-reports/security-test-2026-08-28T08-24-16-652Z.{txt,html,json}. NOT covered by this automated pass (tracked separately in Pending): the Ground School Progress IDOR fix (client-side-only, needs a manual browser check with a second student account) and Direct Exam Entry's positive/allowed-role path (no safe automated cleanup path). | 2026-08-28 (session 7 cont.)
43 | Testing | E2E testing round — role-gated dashboard widgets | StudentProgressWidget/NotificationWidget gated on STUDENT_ROSTER_VIEW_ROLES; a 403 for non-roster roles had been rendering a false-positive "All students are progressing well!". | 2026-08-29
44 | Quality | SWR migration — Stages 1-8 | Availability, Instructors, Students, Flight Records, Scheduled Flights, Maintenance, Holidays, FTO Settings/Sortie Types/Exercises moved off the Zustand store onto SWR hooks in lib/hooks/. See claude/swr-migration-plan-2026-08-28.md. | 2026-08-28 → 2026-09-02
45 | Feature | Safety Management workflow | 5x5 ICAO risk matrix, OPEN → RESOLVED → CLOSED lifecycle, corrective actions, year-scoped incident numbering (INC-2026-NNN), auto-routing of technical categories to Maintenance, three-tier report/manage/resolve permission split. Live-tested end to end. | 2026-09-01 (9c881f7, 39c98e2)
46 | Feature | Pilot-facing squawk / defect reporting | "Report a Defect" page for instructor/student roles writing into maintenance_records, with the server forcing every staff-only field regardless of client input. | 2026-09-01 (9c881f7)
47 | Feature | Instructor Duty Hours visibility view | Today / trailing-7-day hours vs each instructor's Max Daily Hours, with an over-limit badge. DELIBERATELY non-regulatory — DGCA FTL CAR was researched and found scoped to commercial air-transport crew, not FTO instructors. | 2026-09-01 (9c881f7)
48 | Feature | Drag-and-drop calendar rescheduling | UX enhancement to the booking board. | 2026-09-01
49 | Feature | RMT/IMT maintenance ticket numbering | Year-scoped RMT-<year>-NNN (staff-logged) and IMT-<year>-NNN (pilot squawk) counters sharing one ticket_number column. NOTE: had been reported as committed in an earlier handoff doc but never actually was — caught by git status. | 2026-09-03 (5289995)
50 | Quality | Repo cruft removal | 58 stray .patch files (1.38MB, 57 of them untracked and therefore invisible to git status), two dead backup scripts, and a duplicate postcss config. Repo root: 120 entries → 60. | 2026-09-03 (3dbb170)
51 | Quality | cleanup/dead-code branch — store trim, dead email path, Zustand removed | lib/store.ts 643 → 283 lines; deleted sendWelcomeEmail/sendPasswordResetEmail and the unused /api/send-email route (which could send arbitrary HTML from the org Resend key); Zustand removed entirely, replaced by SWR hooks + useSyncExternalStore for theme. -465 net lines, one dependency gone. | 2026-09-05 (79dac0d)
52 | Bug fix | NOAA visibility parsed as NaN — safety warnings silently dead | NOAA returns visib as the STRING "6+"; the truthy guard let "6+" * 1609.34 = NaN through, and every NaN < threshold comparison is false — so "Reduced visibility" and "Low visibility" warnings could never fire. Shared visibilityMeters() parser at both call sites. | 2026-09-05
53 | Bug fix | IST date handling — 13 sites reviewed individually (item 51) | toISOString().split("T")[0] reads a Date back in UTC, wrong by a day for local-midnight Dates always, and for "today" between 00:00-05:30 IST. New lib/ist.ts (toDateStr/todayIST/daysFromTodayIST). ⚠️ Two bugs in computeMaintenanceDueItems CANCELLED each other — fixing either alone would have broken working due/overdue flags. Tested inside the real 01:00 IST failure window. | 2026-09-05
54 | Bug fix | Honest empty states — NOTAM tile and flight-modal readiness | Four-state NOTAM tile (no station / loading / error / empty) and tri-state weather readiness. ⚠️ The first attempt made things WORSE — it rendered "No active NOTAMs" while the service 500'd, because fetchNOTAMs swallowed errors and returned []. Root fix was in the fetcher (throw), not the tile. | 2026-09-05
55 | Feature | SkyLink NOTAM API integration | Replaced the discontinued aviationweather.gov NOTAM endpoint. Server-side notam_cache table, tunable notam_cache_ttl_hours FTO setting (clamped 1-24h, default 2h ≈ 360 calls/month against a 1,000 free tier), x-notam-cache response header. ⚠️ The cache write was originally fire-and-forget and silently never completed on Vercel — a serverless function can be frozen the instant it returns. | 2026-09-05
56 | Feature | ICAO / latitude-longitude mutual exclusivity (item 78) | Lat/long inputs disabled while an airport code is set; values kept, not cleared. | 2026-09-05
57 | Security | /api/notam authentication (item 79) | requireSession() runs FIRST, before the API-key check and any settings read, so an unauthenticated caller cannot even probe whether the integration exists. Each distinct ?station= had been costing a metered upstream call. | 2026-09-05 (6d8e623)
58 | Compliance | NOTAM provenance disclaimer | Dashboard tile, flight modal and print brief: "Source: SkyLink (FAA SWIM feed). Situational awareness only — not an official briefing. Verify with AIM India before flight." SkyLink redistributes the FAA feed; AAI/AIM India is the authoritative Indian source. | 2026-09-05
59 | Bug fix | "Refresh Weather" was a silent no-op (item 71) | Two module-level Map caches in lib/weather.ts (29min METAR, 15min general) returned cached objects to SWR's mutate(), so the button did nothing. Both deleted — SWR already caches per tab. The shared general_weather_cache DB table stays; that one is cross-user. | 2026-09-09 (1c23781)
60 | Quality | Admin Setup CRUD-tab consolidation — ConfigTable (item 73) | Shared components/admin/ConfigTable.tsx replaces the duplicated list/form/delete shape in Roles, Sortie Types, Ground School and Training Programs. 1,077 → 642 lines (-435). All four verified in-browser: add/edit/cancel/update/delete plus uppercase, nullable, float and integer round-trips. Exercises/Requirements/Maintenance Schedule/Aircraft/Users/Holidays/Settings deliberately NOT converted. | 2026-09-09 (3c51167)
61 | Feature | DGCA Maintenance Log — full implementation (backlog #3) | add-dgca-maintenance-log-fields.sql: parts_used, ame_name, ame_license_no, crs_reference, is_baseline. Release-to-Service block on the Log Maintenance form (COMPLETED records only; squawk path forces all four null server-side). New /dashboard/reports/maintenance-log with PDF + styled XLSX export. Airframe hours REUSE hobbs_at_completion rather than adding a second source of truth. | 2026-09-09 (bab16be, c3fe856)
62 | Compliance | is_baseline — synthetic rows kept OUT of the DGCA register | "Set Baseline" writes a COMPLETED maintenance_records row purely to anchor an item's due clock — no work performed, nobody certified anything. Eight of eleven rows in the first working report were these. Excluded on a real COLUMN, not on the description text, because a compliance filter must not depend on UI copy. 11 rows → 3. | 2026-09-09
63 | Quality | exceljs → write-excel-file | exceljs pulled ~96 transitive packages (inflight, glob@7, rimraf@2, fstream — several EOL) plus 2 moderate advisories, to write one styled worksheet. Swapped for write-excel-file (1 runtime dep). npm audit: 2 moderate → 0. Gained landscape orientation. | 2026-09-09 (c3fe856)
64 | Bug fix | Duplicate /api/students per Dashboard load (items 81, 53) | fetchFlightRecords → mapFlightRecordRows calls fetchStudents() DIRECTLY to bake in the studentName join — invisible to SWR, which cannot dedupe a call it never sees. Fixed with an in-flight PROMISE dedupe (cleared on settle, so it can never serve stale data — unlike the item-71 caches). Also gated the Dashboard's own ungated useStudents(), which had been firing a doomed 403 for maintenance roles. 2 requests per load → 1. | 2026-09-09 (3f80963)
65 | Docs | Corrected a wrong comment in AuthProvider.tsx | It claimed dedupingInterval:5000 makes "two mounts of the same key within 5s share one request". It does not — SWR clears a key's dedup entry when the request SETTLES, so the interval only collapses requests overlapping IN FLIGHT. That misreading hid a real double-fetch and misdirected three rounds of analysis. | 2026-09-09
66 | Research | DGCA incident-report legal basis established | No DGCA form is published, but the field list is STATUTORY and public: Aircraft (Accidents and Incidents Investigation) Rules, 2025 — G.S.R. 829(E), 7 Nov 2025, Gazette Extraordinary Part II-Sec 3-Sub-sec (i), under the Indian Aircraft Act 2024. Rule 4(2) prescribes 11 notification items, unchanged in substance from the 2017 Rules (G.S.R. 1011(E)). Adds a hard 24-hour deadline and notification to AAIB + DGCA + District Magistrate + police. | 2026-09-10
67 | Research | AIM India NOTAM API — definitively does not exist | AAI publishes no NOTAM API: eAIP/AIP as HTML+PDF, monthly NOTAM summary PDFs, current NOTAMs behind the login-gated Automatic Self Briefing System, and AFTN (a telecom circuit, not an app integration). No SWIM entry, no AIXM service, no developer portal. Official-source path is a written request to gmais@aai.aero. DO NOT RE-RESEARCH. | 2026-09-05
68 | Bug fix | Quick-reschedule buttons left a stale OVERDUE state (09-05 open-items list, item 66) | ROOT CAUSE FOUND. updateMaintenanceRecord() spliced the PATCH body into the SWR cache with {revalidate:false}. isOverdue and daysUntilDue are DERIVED in fetchMaintenanceRecords from maintenanceEnd/scheduledDate/status, so the splice copied the new end time but left the derived fields at their fetch-time values: the window text moved, the red row and OVERDUE badge did not. Same bug hit Complete (a completed record kept its overdue styling). Fixed by revalidating instead of recomputing the derivation in a second place. VERIFIED LIVE 2026-09-11 on a throwaway record (since deleted): +4h moved 11:00->15:00 and correctly stayed OVERDUE (still past); two +1d clicks pushed the end 40 min into the future and the badge and red row cleared with no refresh. NOTE: the buttons only render when a record has a maintenanceEnd — none of the current live records do, so on production data they are invisible, which may be part of the original report. | 2026-09-11
69 | Feature | Consolidated DGCA audit-pack export | One PDF for a date range: every saved Daily Flying Report, the BA register rollup, and the Maintenance Log per aircraft with completed work. New page /dashboard/reports/audit-pack + card on the Reports landing page. lib/pdf.ts: the four existing generators each take an optional trailing doc and return it (section()/finish() helpers), so a section appends as new pages instead of downloading separately; the four existing call sites are unchanged. Orientation is per-page, so the landscape Maintenance Log coexists with the portrait reports. generateBreathAnalysisReport's period union gained 'Custom' — labelling an arbitrary range 'Monthly' on a regulator-facing page would be false. Missing days are NOT auto-generated (that would write saved reports as a side effect of an export) — they are listed on screen and printed on the cover. Range capped at 92 days. VERIFIED LIVE 2026-09-11: 4-page pack, cover counts matched an independent data query, all 30 gap dates printed, orientation correct, both range guards working, no app-side console or network errors. | 2026-09-11
70 | Feature gap | Maintenance Log header — Log Book Serial No. and CAMO/AMO Approval No. | MOVED FROM PENDING (was row 21) — shipped 2026-09-10 in commit 6858b33 and never moved out of Pending. aircraft.log_book_serial_no + fto_settings key camo_approval_no, migration add-logbook-and-camo-refs.sql (applied). Both are UNVALIDATED PLACEHOLDERS: the report omits the whole header line when they are blank rather than printing an empty label. Still blocked on a real log book cover page and a real CAMO/AMO approval certificate; expected change is labels only, not storage. | 2026-09-10 (6858b33)
71 | Security | Cron job silent-failure fallback to anon key | MOVED FROM ON HOLD (was row 11) — closed 2026-09-10 in commit b55797a and never moved. lib/supabase-admin.ts no longer falls back to the anon key when SUPABASE_SERVICE_KEY is missing; the old behaviour returned 200 with RLS-filtered (usually empty) data instead of failing. Deliberately still does not throw at module load, because next build imports these modules and a build-time env gap would fail the deploy. | 2026-09-10 (b55797a)
72 | Feature | Projected finish from actual flying rate (progression, phase 1) | lib/training-pace.ts + lib/training-pace.test.ts, shown as one line under the Progress page metric cards. Projects time-to-target from hours flown in a trailing 56-day window. CORRECTS A WRONG PREMISE: the comparison doc called pace-vs-target 'a computed view over data we already have'. It is not — training_programs has NO course duration and students.joinedDate is optional and null on every current row, so there is no required pace to compare against. This measures what the data does support. Returns null when no total-hours target is configured (same convention as requirementPercent). Reports sample size with every rate so 2 flights are not read as a trend; caps at 2 years and suppresses the date rather than projecting into the 2040s; a student who flew then stopped reads as STALLED with their last flight date, which is the case worth acting on. VERIFIED LIVE 2026-09-11: Dummy Student (3h of 200h, 2 flights) rendered '0.4h/week — over 2 years to target at this rate (2 flights in 8w)' — the far-off guard firing on real data; Dummy Student Two rendered 'No flights recorded yet'. tsx test, tsc and lint all clean. | 2026-09-11
73 | Accessibility | A 16th modal had no Escape handling — MaintenanceDueSection | Found during the 2026-09-11 verification pass by re-grepping every `fixed inset-0` overlay rather than trusting the documented count of 15. LogMaintenanceItemModal (Set Baseline / Log Completion) had click-outside and a labelled Close button, so it LOOKED complete — only Escape was missing, and only a keyboard user would ever have noticed. All 16 overlays now call useEscapeToClose. Verified by re-audit; the modal itself is not reachable to click-test while MaintenanceDueSection renders null. | 2026-09-11
74 | Accessibility | Accessibility-hardening round — VERIFIED, including with a real screen reader | CLOSES THE OLDEST URGENT ROW (open since session 7, ~3 weeks). ESCAPE: 13 of 16 overlay modals confirmed on real keypresses against the running app; the count itself was wrong and a 16th uncounted modal was found and fixed (see Completed 73). SCREEN READER: Narrator run by the user 2026-09-11 on FlightRecordForm's close control — announced "Close, button", so the aria-label DOES reach the accessibility tree. The other 14 Close buttons use byte-identical markup (aria-label="Close") and GroundSchoolCalendar's toast uses aria-label="Dismiss notification"; all confirmed in source. SCOPE, STATED PRECISELY: one control verified by ear, fifteen by identical markup. The MECHANISM is proven — this is no longer an untested claim. Three modals remain unreachable to click-test for structural reasons, tracked separately in Pending, as is a newly-found focus-management gap. | 2026-09-11
75 | Security | ground_school_enrollment writes moved behind gated server routes (item 39, the last of the 2026-08-24 review's direct-write findings) | Six write sites went straight to Supabase on the public anon key with no role check: four on the Ground School Attendance page (attendance status, five exam fields, add student, remove student) and two in syncGroundSchoolFromChecklist(). The page's RoleGate decided what RENDERED, not what the database accepted. Adds app/api/ground-school/enrollment (POST/PATCH/DELETE, GROUND_SCHOOL_WRITE_ROLES) and app/api/ground-school/checklist-sync (POST, REQUIREMENTS_WRITE_ROLES), both on supabaseAdmin. THE PATCH FIELD WHITELIST IS THE POINT: updateExam() passed an arbitrary column name through as {[field]: value}; a route forwarding that verbatim would be an arbitrary-column-write primitive carrying the SERVICE-ROLE key — worse than what it replaced. Five columns accepted; class_id/student_id excluded so no caller can re-point one student's record onto another. DGCA roll-number rule now enforced server-side too. ROLE SETS PRESERVED EXACTLY — GROUND_SCHOOL_WRITE_ROLES is the attendance page's previously-INLINE array, now shared so page and route cannot drift. This moved WHERE the check happens, not WHO passes it. VERIFIED LIVE 2026-09-16 as dummy.operations: enrollment route ADMITS operations (404 on a missing row = cleared the gate, wrote nothing), checklist-sync REJECTS operations (403) — both directions of the role split proven in one session. Also verified as super_admin: whitelist rejects a bad column (400), six validation paths correct, DGCA guard does a real lookup, checklist-sync lifecycle created/unchanged/deleted. NOT VERIFIED: the attendance page's four UI paths — there are zero ground school classes in the data, so nothing to act on. Route contract + typecheck only. | 2026-09-16 (8eaeb6b)

## Pending
# | Area | Item | Details | Urgency
1 | Security | Manually verify remaining security-hardening items (IDOR + direct-exam positive path) | Automated round (all 8 Admin Setup config tables, Aircraft Setup, Direct Exam Entry negative path) passed 114/114 against production on 2026-08-28 — see Completed and scripts/security-test-reports/. Two items still need manual verification because they can't be safely automated: (1) the Ground School Progress IDOR fix (?student= URL override) — a client-side React guard with no server-observable difference, needs a real browser click-through with two distinct student accounts (only one dummy student account has been provided so far — a second is needed to actually exercise this); (2) the Direct Exam Entry route's positive/allowed-role path — no DELETE endpoint and no FK-existence check on the insert, so a successful call can't be cleanly undone; verify manually and clean up the resulting ground_school_enrollment row by hand if exercised. | Normal
3 | Permissions | Test My Students instructor-only scoping | Confirm admin/super_admin get Not Authorized on /dashboard/instructor; instructors still see it and it works. | High
4 | UI | Test Dashboard after Quick Actions removal | Confirm layout still looks right and every removed tile's destination is still reachable via the sidebar for each role. | High
5 | Testing | Full smoke-test pass | Training-stage dropdown, student cards, students-list filter, target-hours consistency, Multi Engine/Simulator progress cards, Breath Analyser Register + Report end-to-end, instructor CPL server-side block, SPL/CPL issue-date fields. | Normal
6 | Testing | Permission override feature — no live test yet | Per-user module access overrides have never been tested end-to-end in the live app. | Normal
7 | Testing | QA Addendum B not run against real app | Doesn't yet cover Reports or any 2026-08-19 onward work. | Normal
8 | Testing | Confirm Safety Officer user actually exists | User reported creating one but it hasn't been independently re-verified. | Normal
9 | Testing | Test instructor CPL server-side block | Not yet explicitly confirmed that a blank CPL number is rejected server-side. | Normal
10 | Testing | Test SPL/CPL auto-expiry + alert system | Issue-date auto-fill/override behavior, and the expiry badge + email alert system. | Normal
11 | Testing | Test target-hours consistency for a MULTI student | Dashboard widget / Progress page / Instructor dashboard should all agree, now that the MULTI row exists. | Normal
12 | Testing | Retest Partial Weekly Off Day feature | Confirm 29-08-2026 (2nd/4th Saturday rule) is now correctly blocked after the Settings-store-refresh fix — asked but not yet confirmed by the user. | Normal
13 | Testing | Functionally test BA Test Register permission narrowing | Confirm admin/super_admin can no longer add/edit BA entries (view-only) and safety_officer/operations still can, on the real logged-in app. | Normal
14 | Testing | Test Aircraft Maintenance Schedule Phase 1 (IN PROGRESS) | PARTIALLY EXERCISED 2026-09-09: an existing COMPLETED Oil Change record was edited through the normal Log Maintenance form with Hobbs at Completion filled via the new "Use <hobbs>" prefill button, and saved successfully. NOT yet exercised: logging a FRESH completion from scratch through that form and confirming the matching Due-panel item resets. That reset is the exact path the earlier item-name-mismatch bug lived in, so it still deserves a deliberate run. | Normal
15 | Testing | General regression pass over the rest of the app | Booking, Flight Records, Ground School, and the other Admin Setup tabs — nothing in this session's Aircraft Maintenance Schedule work should have touched them, but worth a normal-use sanity check now that everything (schedule feature, Type/Model filtering, fleet expansion, DB-driven engine type) is live on production. | Normal
16 | Testing | Test "Other (custom)" Model warn-and-block behavior | LIVE ON PRODUCTION as of 2026-08-27 (commit e137913), untested. Add/Edit Aircraft, both AircraftFormModal.tsx and the Admin Setup Aircraft tab: pick "Other (custom)…", confirm the warning shows and Save/Add is disabled; add the model via Admin Setup > Aircraft Maintenance Schedule, click "Refresh list", confirm it now appears and can be picked and saved. Also edit an aircraft with a legacy unmatched Model and confirm the same warning/block appears until it's re-picked. | High
17 | Testing | Maintenance Due panel — verify next-due dates live (item 76) | The IST date-arithmetic fix is verified in isolation but never in the UI, because MaintenanceDueSection renders null while every item is OK. Next time an item goes OVERDUE/DUE_SOON/NO_BASELINE: confirm the displayed due date lands on the true anniversary (an Annual completed 03-09-2026 should read 03-09-2027, not 02-09) and that the status flag is unchanged. SELF-RESOLVING — just needs someone to look when it happens. | Normal
18 | Testing | Cold-start 500 on the first /api/students after a server start | Seen once 2026-09-09: the first request after a dev-server restart returned 500 with the route's own {"error":"Failed to load students."}; SWR's retry got 200 immediately. Not reproducible across four subsequent loads. Probably what item 81 was originally filed as ("a 401 on page load") and probably the same thing as item 53's "transient error on rapid page loads". WATCH ON PRODUCTION — not worth hunting in dev. | Normal
19 | Compliance | ⚠️ GATE — verify the DGCA Maintenance Log layout against the real CAMO register | The report ships with a visible DRAFT FORMAT warning on the page, the PDF and the XLSX. It was built from standard FTO record-keeping conventions plus the statutory column set, NOT from a DGCA-issued form. The warning comes off only when someone compares it line by line against the FTO's CAMO-approved register. NOT A TASK — a gate before first real DGCA-facing use. | High
20 | Compliance | ⚠️ GATE — three test safety-incident records still in production data | User decision 2026-09-05: not cleaning up while production doubles as the testers' evaluation environment. Reasonable pre-launch. BUT the safety incident register is DGCA-facing, and incident_number is generated as "max + 1" — so deleting the highest-numbered rows later makes the next real incident REUSE those numbers. Clean up before any real incident is filed, not after. | High
22 | Accessibility | Modals do not move or trap keyboard focus when they open | FOUND 2026-09-11 during the screen-reader run, and NOT covered by any previous accessibility work. Opening a modal leaves document.activeElement on <body> — confirmed live in the DOM, not inferred. Nothing in the codebase moves focus into a dialog on open, traps it inside while open, or restores it to the trigger on close. For a screen-reader or keyboard-only user that means tabbing through the entire page BEHIND the dialog to reach its controls, and nothing stops focus wandering back out. This is a WCAG 2.1 concern in its own right (2.4.3 Focus Order / 2.1.2 No Keyboard Trap's counterpart), separate from the Escape and aria-label work, which are both now done. Affects all 16 modals, so it belongs in the shared layer — a focus-management hook alongside useEscapeToClose, not 16 edits. NOT a one-line fix; scope it before starting. | High
23 | Security | Ground School Attendance page still READS ground_school_enrollment directly on the anon key | Writes were closed 2026-09-16 (Completed 75); reads were deliberately left alone rather than smuggled into a writes fix. Same shape as the nine remaining unscoped tables — belongs in that effort, not its own row of work. | Normal

## On Hold
# | Area | Item | Details | Why it's on hold
1 | UI/UX | 4 modals' hardcoded dark Tailwind classes | Unreadable in light mode. | Needs visual verification — not fixable blind in a sandbox with no deployed URL.
2 | Security | Two more unhardened write paths | Attendance page's exam editor + RequirementsChecklist's own separate exam-entry path still write client-side into ground_school_enrollment/training_requirements. | Found during session 7's security round but out of the four original numbered findings — same fix shape as direct-exam, different call sites.
3 | UI/UX | 3 modals can overflow on short viewports | Viewport-dependent, needs visual/viewport verification. | Not fixable blind in a sandbox with no browser access.
4 | Code quality | Deferred lint bucket | no-explicit-any, react-hooks/exhaustive-deps, react-hooks/set-state-in-effect, @next/next/no-img-element. | User explicitly chose 'safe batch now, rest later' during the lint cleanup round.
5 | Correctness | 0-vs-null bug in progress percentages | ?? only falls through on null/undefined, not 0 — a legitimate 0 in a training-program hour field produces NaN/100%-clamped results. | Flagged in the whole-frontend review, not yet scheduled.
6 | Correctness | Hardcoded 40h/200h fallback targets | app/dashboard/student/page.tsx hardcodes targets instead of using matchTrainingProgram(); also inconsistent with the Dashboard widget's own fallback. | Flagged in the whole-frontend review, deliberately deferred.
7 | Correctness | Several smaller correctness bugs | Medical-valid null-guard, midnight-crossing flight-duration clamp, fuel-percent zero-guard, Daily Ops Sheet IST minute-drop. | Lower urgency per the whole-frontend review's own framing.
8 | Code quality | CSV import logic duplicated | Drifted between ExercisesTab.tsx and HolidaysTab.tsx. | Flagged in the whole-frontend review, not yet scheduled.
9 | Code quality | GroundSchoolCalendar.tsx is a 1036-line monolith | Candidate for a refactor/split. | Flagged in the whole-frontend review, not yet scheduled.
10 | Code quality | ✅ DONE 2026-09-09 — Admin Setup CRUD-tab boilerplate consolidated | Shared ConfigTable component now backs Roles, Sortie Types, Ground School and Training Programs: 1,077 → 642 lines. Kept here for history rather than deleted. | RESOLVED — see Completed. Still open as a judgment call: whether Exercises and Requirements & Solo Release should join ConfigTable once it has proven itself in production.
12 | Data | Optional: backfill expiry/issue dates | Existing SPL/CPL numbers on file have no expiry/issue date backfilled. | Optional, no user request yet.
13 | Cosmetic | Minor pre-existing inconsistencies | Exercise field storage format differs between FlightRecordForm and BookingForm; a historical flight's exercise short code changed; leave-type list duplicated between two files; a couple of pre-DGCA-fix rows have blank roll numbers; every aircraft's Type/Model should be spot-checked post-restructure. | All low-impact cosmetic items, deliberately not chased.
14 | Correctness | Dashboard/Instructor-dashboard vs Progress page fallback mismatch | 200h vs 40h fallback targets disagree when no training program matches. | Deliberately deferred pending a decision on which fallback is correct.
15 | Quality | GET /api/maintenance-records route not built | Maintenance record READS still go through a legacy direct client-side Supabase call; only writes are routed through the API. Named in backlog item #3 but deliberately left out of the DGCA Maintenance Log commit. | Deliberately deferred 2026-09-09 — unrelated hardening, and folding it in would have meant re-testing every maintenance read inside a compliance commit.
16 | Quality | Other reports still export plain CSV with a misleading label | Daily Flying and BA reports still say "Export Excel/CSV" while emitting CSV, which cannot carry any formatting. The Maintenance Log now exports a real styled .xlsx via write-excel-file. | Deliberately not changed 2026-09-09 — altering three reports inside a commit titled "maintenance log" is how a revert takes out unrelated work.

## New Features (Backlog)
# | Feature | Description | Status | Impact | Effort | Notes / What to decide
1 | Checkbox-style Requirements UI | Friendlier way to manage requirement completion than the current checklist. | Not started | Medium | Medium | Called out in the original backlog as 'the natural next feature once security/testing is cleared.' Smallest, most self-contained of the open backlog items.
2 | DGCA Incident Report — full implementation | Extend the existing safety_incidents table with the draft template's fields (occurrence classification, per-person injury, damage, contributing factors, DGCA notification ref) and build a proper standalone form/page (today it's a small panel on the Daily Flying Report page). | Researched + designed, PARKED by user 2026-09-10 | High | Medium | UNBLOCKED 2026-09-10 — the old blocker ("verify the draft Word template") is GONE. No DGCA form is published, but the field list is STATUTORY: Rules 2025, G.S.R. 829(E) of 7 Nov 2025, Rule 4(2), eleven items, unchanged in substance from the 2017 Rules (G.S.R. 1011(E)). Design agreed: occurrence_class (Accident/Serious Incident/Incident, Schedule A examples as helper text); the eleven Rule 4(2) fields on a block that appears only once classified; notified_at + per-authority tracking (AAIB + DGCA + District Magistrate + police) with the 24-hour clock visible. NO draft-format warning needed — built against cited law. Parked at the user's request, not blocked. Full detail in claude/handoff-2026-09-05.md.
3 | DGCA Maintenance Log — full implementation | Extend the existing maintenance_records table with DGCA-specific fields (airframe hours, block hours, parts used, AME license, CRS reference); also switch loadMaintenanceRecords off its legacy direct-Supabase read while touching this table. | ✅ SHIPPED 2026-09-09 | High | Medium | Delivered: parts_used, ame_name, ame_license_no, crs_reference, is_baseline; Release-to-Service form block; /dashboard/reports/maintenance-log with PDF + styled XLSX. Airframe hours reuse hobbs_at_completion rather than adding a second source of truth. STILL OPEN from this item's original scope: switching maintenance-record READS off the legacy direct-Supabase call (see On Hold), and Log Book Serial No. / CAMO Approval No. (see Pending). Layout keeps a DRAFT FORMAT warning until verified against the real CAMO register.
4 | Mobile PWA (installable/offline) | The responsive-layout half is done (works well on phones/tablets); true installability — manifest, service worker, install prompt, offline support — is not built. | Partially done | Medium | Medium | No explicit user ask yet beyond the original backlog line item.
5 | Billing module | Student/FTO billing and invoicing — no scoping conversation has happened yet. | Not started | High | Large | Needs a scoping discussion before any estimate is meaningful — likely the largest single feature in the backlog. NOTE: the FlightLogger comparison rates this the SINGLE BIGGEST functional gap and the only unresolved P1 — the other three P1s all closed 2026-09-01. Suggested minimum shape there: student ledger table, manual credit/debit tied to flight records, balance badge on the student profile, simple invoice/receipt PDF; payment gateway deferred.
6 | Multi-FTO / multi-base support | The app currently assumes a single operating location/airport; multi-base support isn't built. | Not started | Medium | Large | Touches most of the app's data model (aircraft, schedule, weather/NOTAM, reports) — needs scoping.
7 | Multi-language support | No i18n framework or translated strings exist yet. | Not started | Low | Large | No user demand signal yet beyond the original backlog line item — lowest apparent priority of the five backlog items.
8 | Aircraft Maintenance Schedule — Phase 2 (hard-block bookings) | Auto-ground / block scheduling when a mandatory maintenance item goes overdue, instead of Phase 1's non-blocking warnings. | Not started | Medium | Medium | PRECONDITION NOW MET — Phase 1 has run cleanly in production since 2026-08-27. Still needs the two decisions this row always named: which items (if any) are hard-blocking vs warning-only, and how a false-positive baseline is handled before an aircraft is auto-grounded. The new is_baseline column (2026-09-09) makes synthetic baseline rows distinguishable, removing one obstacle to the second question.
9 | One-time "unrecognized Model" admin banner | A banner/flag (e.g. on Admin Setup or the Aircraft list) when N aircraft have a Model value that doesn't match any maintenance schedule template, with a one-click path to the affected aircraft's Edit form to re-pick the correct Model from the dropdown. | Not started | Low | Small | 2026-08-27 update: new aircraft can no longer be created/saved with an unrecognized Model at all (see Completed) — this item now only covers EXISTING aircraft that predate that fix (or were saved before the DB-driven engine_type migration). Lower priority than originally scoped, since the main failure mode is now closed at the point of entry.
10 | Consolidated DGCA audit-pack export | One export bundling the existing report PDFs — Daily Flying, BA Register/Report, Maintenance Log — into a single inspection-ready pack for a date range. | Built 2026-09-11 | High | Small | Shipped — see Completed 69. Bundles Daily Flying, BA rollup and per-aircraft Maintenance Log into one PDF for a date range. Student logbooks deliberately excluded (per-student, would run to hundreds of pages).
11 | Business insights / analytics dashboard | Fleet utilisation, instructor productivity, and revenue once billing exists. | Not started | Medium | Medium | From the FlightLogger comparison (P2 gap #8). Partly gated on Billing for the revenue half.
12 | Ground School LMS (course content + quizzes) | Ground School schedules classes and records attendance/exams but delivers no content. | Not started | Medium | Large | From the FlightLogger comparison (P2 gap #5). Needs a scoping decision first — could be anything from file attachments to a full quiz engine.
13 | Competency-Based Training & Assessment (CBTA) | Structured competency grading instead of today's exercise complete/incomplete + free-text notes. | Not started | Medium | Large | From the FlightLogger comparison (P2 gap #9). ⚠️ That doc's own caveat: only worth building if DGCA or the FTO SOP actually requires it. Confirm before scoping.
14 | Clarify: can students self-book? | Unclear whether students book their own slots today or staff always book for them. | Question, not a build | Low | Small | From the FlightLogger comparison (P3 gap #10). A five-minute answer that may or may not create work.
15 | Internal messaging / shared document library | No in-app messaging or document store. | Not started | Low | Medium | From the FlightLogger comparison (P3 gap #12). The doc's own note: a simple Documents tab under Admin Setup would cover most of the need.
16 | Plan-based pace (progression, phase 2) | Required-pace-vs-actual against a plan, the FlightLogger Student Progression parity half. NEEDS DATA THAT DOES NOT EXIST: an expected duration on training_programs (additive migration) and a joinedDate on every student (currently null on all). Build it ALONGSIDE the phase-1 projection, not instead of it — 'behind plan' and 'not flying at all' are different problems with different fixes. | Blocked on data + a decision | Medium | Medium | Decide what course durations the FTO actually commits to before building. Shipping it first would have rendered empty for every student, the same trap as the Maintenance Due panel (item 76).

## Summary
Plan Tracker — Summary
Updated 2026-09-16. Previous update 2026-09-11.
Completed items | 75 | was 67 on 2026-09-10
Pending (needs verification) | 21 | accessibility round closed; focus-management gap opened in its place
— of which Urgent | 0 | THE ACCESSIBILITY ROW IS CLOSED as of 2026-09-11 — screen reader run, Escape verified. No Urgent rows remain.
— of which High | 5 | +1: modal focus management (new, 2026-09-11)
On Hold / deferred | 15 | was 16; cron anon-key fallback moved to Completed (closed 09-10, never moved)
New Features in backlog | 16 | audit pack Built; plan-based pace added as phase 2
What changed since the last update
SHIPPED: SWR migration (8 stages), Safety Management workflow, squawk reporting, Duty Hours, drag-and-drop rescheduling, RMT/IMT numbering, repo cruft removal, Zustand removal, IST date fixes, NOAA visibility fix, SkyLink NOTAM integration + auth + disclaimer, ConfigTable consolidation, DGCA Maintenance Log, exceljs→write-excel-file, /api/students dedupe, DGCA audit-pack export, quick-reschedule stale-state fix, projected-finish progression (phase 1) ground_school_enrollment gated routes (item 39 closed).
UNBLOCKED: DGCA Incident Report — the statutory field list was found (G.S.R. 829(E)); parked by choice, not blocked.
RESOLVED FROM ON HOLD: Admin Setup CRUD-tab boilerplate.
Suggested next steps, in order
1. ~~ACCESSIBILITY TESTING~~ — DONE 2026-09-11. Escape verified on 13 of 16 modals, a 16th uncounted modal found and fixed, and Narrator confirmed "Close, button". NEW IN ITS PLACE (High, not Urgent): modals do not move or trap focus when they open — see Pending 22.
2. The two compliance GATES (new, High). Neither is a build: verify the Maintenance Log layout against the real CAMO register so its DRAFT warning can come off, and decide on the three test incident records before a real incident is filed (incident_number is max+1, so late deletion causes number reuse).
3. DONE 2026-09-11 — the audit-pack export shipped and was verified live. Next cheapest wins: pace-vs-target progression (a computed view over data FPM already holds, and FlightLogger parity), then the empty-table placeholder on the Daily Flying PDF.
4. Clear the remaining verification Pending rows — My Students scoping, Dashboard post-Quick-Actions, the smoke-test pass, and the fresh-completion Maintenance Due reset test (item 14, only partially exercised).
5. Then pick ONE large feature and scope it properly: Billing (the only unresolved P1 in the competitive analysis, and the biggest functional gap) or the parked DGCA Incident Report (design agreed, statutory basis established — a schema + form pass).
6. Maintenance Schedule Phase 2 is unblocked by its own precondition but still needs two decisions: hard-block vs warning-only per item, and false-positive baseline handling.
7. Still parked: Mobile PWA installability, Multi-FTO/multi-base, Multi-language, the unrecognised-Model banner (mostly obsolete), Ground School LMS, CBTA.
⚠️ TWO NUMBERING SCHEMES — do not conflate them
The handoff docs' "item NN" numbers come from the open-items list in claude/handoff-2026-09-05.md. This sheet's Completed # column is a SEPARATE sequence. Handoff "item 66" (quick-reschedule buttons) is Completed row 68 here; Completed row 66 is unrelated (DGCA incident-report research). Same clash exists for items 5, 36, 42 and 73.