## Summary
FlightLogger vs FlightPro Manager — Competitive Gap Analysis
Generated | 2026-09-10, updated 2026-09-11
FlightPro Manager state | working tree ahead of cf3e172 (main); 72 completed tracker items
FlightLogger source | flightlogger.net/platform, GetApp, Software Advice, afm.aero release coverage
SUPERSEDES | the 2026-08-31 workbook, whose status column was a 2026-08-27 snapshot
Features compared | 53
Built | 25
Partial | 7
Not Built | 20
Not applicable | 1
Previous analysis (08-27 snapshot) | 18 Built / 4 Partial / 24 Not Built of 46
Movement | 3 of 4 P1 gaps closed; billing is the only P1 left. Report pack closed 2026-09-11.
Ahead of FlightLogger | NOTAM+METAR dashboard, BA test register, DGCA Maintenance Log, PIC/PICUS tracking, maintenance ticket numbering, per-user permission overrides
New FlightLogger features since 08-31 | Combined Syllabus Builder (Jun 2026), Float Time Logging (Jun 2026, N/A here), Student Progression module (Nov 2025 add-on)
CAVEAT | Compares against FlightLogger's PUBLICLY ADVERTISED feature set — marketing pages and directory listings, not their actual product. Features may be shallower or deeper than advertised.

## Missing Features
Priority | Feature | Area | Status | FlightLogger Has It | Note / What To Decide
P1 | Student account balance / prepaid hours | Finance | Not Built | Yes (User Balance Module) | THE ONLY P1 LEFT. Largest functional gap versus FlightLogger.
P1 | Invoicing | Finance | Not Built | Yes | No invoice generation anywhere.
P1 | Payment processing | Finance | Not Built | Implied | No payment collection.
P2 | Student Progression / pace-vs-target monitoring | Student & Training | Partial | Yes (add-on, Nov 2025) | PARTIAL. The projection half is built; the plan half is not, and CANNOT be without new data: training_programs has no course duration and students.joinedDate is optional and currently null on every row. Phase 2 adds both. Note this row previously claimed pace-vs-target was 'a computed view, not new data' — that was wrong.
P2 | Competency-Based Training & Assessment (CBTA) | Student & Training | Not Built | Yes (CBTA Pro) | Only worth building if DGCA or FTO SOP requires it. Confirm before scoping.
P2 | Learning Management System (content, quizzes) | Student & Training | Not Built | Yes | Real gap if in-app content delivery is wanted. Needs a scoping decision first.
P2 | Hard enforcement — block booking an overdue aircraft | Aircraft & Maintenance | Not Built | Implied | Phase 2. Precondition now met (Phase 1 clean in production since 08-27). Needs two decisions: which items hard-block, and how a false-positive baseline is handled before auto-grounding.
P2 | Business Insights / analytics | Finance | Not Built | Yes | No fleet-utilisation, instructor-productivity or revenue dashboards. Revenue half gated on Billing.
P3 | Online self-service booking (student-initiated) | Scheduling & Operations | Partial | Yes | Still unresolved: whether students can create their own bookings. A five-minute answer that may or may not create work. Backlog #14.
P3 | Room / simulator / resource booking | Scheduling & Operations | Partial | Yes | No generic classroom/room booking; could reuse the aircraft flow if needed.
P3 | Flight Time Limitation (FTL) / duty tracking | People / Instructors | Partial | Yes | DELIBERATELY non-regulatory. DGCA FTL CAR was researched and found scoped to commercial air-transport crew, not FTO instructors. Reclassify only if DGCA confirms otherwise.
P3 | Audit trail | Safety | Partial | Yes | No general-purpose audit log across all tables.
P3 | Digital sign-offs on lessons/exams | Compliance & Reporting | Partial | Yes | Functionally a sign-off and an audit trail; not an e-signature artifact.
P3 | Dedicated mobile app / PWA | Technical / Platform | Partial | Yes (mobile access) | Installability (manifest, service worker, offline) not built.
P3 | Calendar sync (Google/Outlook) | Scheduling & Operations | Not Built | Yes | No external calendar sync. Integration feature, not a daily-ops gap at this scale.
P3 | Recurring / automated scheduling | Scheduling & Operations | Not Built | Yes | No recurring-lesson templates.
P3 | Combined flight + ground syllabus in one program | Student & Training | Not Built | Yes (NEW Jun 2026) | NEW FlightLogger feature since the last analysis. Low urgency — the data exists in both modules, only a unified view is missing.
P3 | AI-powered performance summaries | Student & Training | Not Built | Yes | Progress shown as raw hours/percentages.
P3 | Employee timesheets | People / Instructors | Not Built | Yes | No staff timesheet/payroll-style logging.
P3 | DGCA Incident Report (statutory fields) | Compliance & Reporting | Not Built | N/A (region-specific) | Researched, designed and PARKED by the user 2026-09-10. Legal basis established: G.S.R. 829(E), Rule 4(2), eleven notification items. Unblocked whenever it is picked up.
P3 | Customizable / user-built report templates | Compliance & Reporting | Not Built | Yes | Adding a report type needs a code change.
P3 | Accounting integration (QuickBooks) | Finance | Not Built | Yes | Defer well past a basic ledger.
P3 | Internal messaging / announcements | Communication | Not Built | Yes | No in-app messaging.
P3 | Document / content library | Communication | Not Built | Yes | A simple Documents tab under Admin Setup would cover most of the need.
P3 | Public API for integrations | Technical / Platform | Not Built | Yes | No documented public API.
P3 | Single sign-on (SSO) | Technical / Platform | Not Built | Yes | No SAML/OAuth org login.
P3 | Multi-location / multi-campus | Technical / Platform | Not Built | Yes | Touches most of the data model. Not needed unless the FTO opens a second base.
P3 | Checkbox-style Requirements UI | Student & Training | Not Built | — | Backlog #1. Friendlier requirement completion than today's checklist. Smallest self-contained backlog item.
P3 | Multi-language support (i18n) | Technical / Platform | Not Built | — | Backlog #7. No framework, no translated strings. No demand signal yet — lowest priority.
P3 | One-time 'unrecognized Model' admin banner | Aircraft & Maintenance | Not Built | — | Backlog #9. Only covers EXISTING aircraft predating the warn-and-block fix; new ones can no longer be saved with a bad Model.
P3 | GET /api/maintenance-records route | Technical / Platform | Not Built | — | Maintenance READS still go through a legacy direct client-side Supabase call; only writes are routed through the API.
P3 | Log Book Serial No. / CAMO Approval No. — real values | Compliance & Reporting | Not Built | — | Placeholder fields shipped 2026-09-10. BLOCKED on the user's real log book cover and CAMO/AMO approval certificate.
P3 | Other reports still export CSV labelled 'Excel' | Compliance & Reporting | Not Built | — | Daily Flying and BA reports emit CSV while saying Excel/CSV. Maintenance Log already exports real styled .xlsx.

## Pending Verification
Urgency | Area | Item | Detail
Urgent | Accessibility | Screen-reader verification of modals and Close buttons | CODE FIXED 2026-09-10 (4964989) — ConfirmDialog Escape + a shared listener stack + 5 missing aria-labels. PARTIALLY VERIFIED 2026-09-11: Escape confirmed closing the Maintenance edit modal in a real browser. STILL OPEN: the other 14 modals, and no screen reader has been run at all — accessible names were checked in the accessibility tree only. Do not mark this verified on tree inspection alone.
High | Compliance | GATE — verify DGCA Maintenance Log layout against the real CAMO register | Report ships with a DRAFT FORMAT warning on page, PDF and XLSX. Built from convention + the statutory column set, not a DGCA-issued form. Warning stays until verified.
High | Compliance | GATE — three test safety-incident records still in production | incident_number is 'max + 1', so deleting the highest rows later makes the next real incident REUSE those numbers. Clean up before any real incident is filed.
High | Testing | Aircraft Model 'Other (custom)' warn-and-block | Live on production since 2026-08-27, untested. Both AircraftFormModal and the Admin Setup Aircraft tab.
High | Testing | Dashboard layout after Quick Actions removal | Confirm every removed tile's destination is still reachable via the sidebar, per role.
Normal | Testing | PICUS on the Debrief form | Shipped 2026-09-10. Identical code to the Flight Record form path, which IS verified. Needs a scheduled flight to debrief.
Normal | Testing | Per-user permission overrides | Never tested end to end in the live app.
Normal | Testing | Full smoke-test pass | Training-stage dropdown, student cards, list filter, target-hours consistency, Multi/Sim progress cards, BA Register + Report end to end, instructor CPL server-side block.
Normal | Security | Remaining hardening items (IDOR + direct-exam positive path) | Automated round passed 114/114 against production 2026-08-28. These two need a manual browser check with a second student account.
Normal | Testing | Maintenance Due panel — next-due dates live | IST date fix verified in isolation, never in the UI. MaintenanceDueSection renders null while every item is OK — needs an item to go OVERDUE/DUE_SOON.
Normal | Testing | SPL/CPL auto-expiry + alert system | Issue-date auto-fill/override, expiry badges, email alerts.
Normal | Testing | Target-hours consistency for a MULTI student | Dashboard widget / Progress page / Instructor dashboard should agree.
Normal | Testing | Partial Weekly Off Day retest | Confirm the 2nd/4th Saturday rule blocks correctly after the settings-refresh fix.
Normal | Testing | BA Register permission narrowing | Confirm admin/super_admin are view-only and safety_officer/operations can still write.
Normal | Testing | Instructor CPL server-side block | Not explicitly confirmed that a blank CPL number is rejected server-side.
Normal | Testing | Safety Officer user exists | Reported created, never independently re-verified.
Normal | Testing | QA Addendum B against the real app | Doesn't yet cover Reports or any 2026-08-19-onward work.
Normal | Testing | General regression pass | Booking, Flight Records, Ground School, remaining Admin Setup tabs.
Normal | Bug | Cold-start 500 on first /api/students after server start | Seen once 2026-09-09, not reproducible across four subsequent loads. Watch on production.
Normal | Compliance | NOTAM disclaimer in the printed briefing | Restored 2026-09-10 and verified in source only — that markup renders only when NOTAMs are active.

## Comparison
Category | Feature | FlightLogger | FPM Status | What FlightPro Manager Has Today | Gap / Note
Scheduling & Operations | Aircraft / instructor / student scheduling | Yes | Built | Schedule Board + Booking Form with double-booking, weekly-off, occurrence-based partial weekly-off and holiday conflict checks, via one shared getSchedulingBlockReason(). | Matches.
Scheduling & Operations | Drag-and-drop calendar rescheduling | Yes | Built | Shipped 2026-09-01. | CLOSED since the 08-27 snapshot, where this was Not Built.
Scheduling & Operations | Online self-service booking (student-initiated) | Yes | Partial | Students have their own login and can view schedule/progress. Instructor self-booking permission exists. | Still unresolved: whether students can create their own bookings. A five-minute answer that may or may not create work. Backlog #14.
Scheduling & Operations | Calendar sync (Google/Outlook) | Yes | Not Built | — | No external calendar sync. Integration feature, not a daily-ops gap at this scale.
Scheduling & Operations | Recurring / automated scheduling | Yes | Not Built | Every booking created individually. | No recurring-lesson templates.
Scheduling & Operations | Room / simulator / resource booking | Yes | Partial | Aircraft with an is_simulator flag can be booked. | No generic classroom/room booking; could reuse the aircraft flow if needed.
Scheduling & Operations | Ground-school class scheduling | Yes | Built | GroundSchoolCalendar with the same weekly-off/holiday rules. | Matches.
Scheduling & Operations | Weather / NOTAM on dashboard | Not advertised | Built | SkyLink (FAA SWIM) NOTAM integration with server-side cache + tunable TTL, METAR/TAF widget, four-state honest empty states, provenance disclaimer. | AHEAD. Not in FlightLogger's advertised set.
Student & Training | Student profiles / centralized records | Yes | Built | Full profile: contact, DOB, medical, SPL, training stage, documents. | Matches.
Student & Training | Syllabi / training programs per course | Yes | Built | Training Programs (PPL/CPL/IR/Multi) with per-program hour minimums, admin-configurable. | Matches, DGCA-tailored.
Student & Training | Combined flight + ground syllabus in one program | Yes (NEW Jun 2026) | Not Built | Training Programs and Ground School are separate modules with separate progress views. | NEW FlightLogger feature since the last analysis. Low urgency — the data exists in both modules, only a unified view is missing.
Student & Training | Student Progression / pace-vs-target monitoring | Yes (add-on, Nov 2025) | Partial | Progress page shows a PROJECTED FINISH from the rate actually flown over a trailing 8 weeks, with sample size, a stalled flag, and a 2-year cap. Shipped 2026-09-11. | PARTIAL. The projection half is built; the plan half is not, and CANNOT be without new data: training_programs has no course duration and students.joinedDate is optional and currently null on every row. Phase 2 adds both. Note this row previously claimed pace-vs-target was 'a computed view, not new data' — that was wrong.
Student & Training | Requirements / stage-check tracking | Yes | Built | Requirements Checklist per student, DGCA roll number + exam score at 3 entry points, blocksSolo gating. | Matches.
Student & Training | Real-time grading / debrief per flight | Yes | Built | Debrief form with exercise grading; Flight Records store sortie detail. | Matches at pass/fail-plus-notes level.
Student & Training | Competency-Based Training & Assessment (CBTA) | Yes (CBTA Pro) | Not Built | Exercise complete/incomplete + free-text debrief notes. | Only worth building if DGCA or FTO SOP requires it. Confirm before scoping.
Student & Training | Learning Management System (content, quizzes) | Yes | Not Built | Ground School tracks attendance and DGCA exam results only. | Real gap if in-app content delivery is wanted. Needs a scoping decision first.
Student & Training | AI-powered performance summaries | Yes | Not Built | — | Progress shown as raw hours/percentages.
Student & Training | Digital student logbook (export) | Yes | Built | generateStudentLogbook() PDF, now reporting solo AND PIC hours separately. | Matches.
Student & Training | PIC / PICUS hour tracking | Not advertised | Built | Instructor can mark a dual sortie as student-PIC and log PICUS hours; PIC = solo + PICUS, shown on the Progress card with the split. | AHEAD, shipped 2026-09-10. DGCA-specific; a generic digital logbook does not model PICUS.
Student & Training | License / medical expiry tracking + alerts | Yes | Built | SPL/CPL auto-expiry from issue date, DGCA age-based Class 1 medical rules, UI badges + cron email alerts. | Matches, and more India-specific than FlightLogger's generic tracking.
People / Instructors | Instructor profiles & certification tracking | Yes | Built | Instructor records with CPL number, issue/expiry, ratings. | Matches.
People / Instructors | Role-based permissions | Yes | Built | 10+ roles plus PER-USER permission overrides, single source of truth in lib/permissions.ts. | AHEAD of a typical fixed-role model. Note: overrides still have no live end-to-end test.
People / Instructors | Employee timesheets | Yes | Not Built | — | No staff timesheet/payroll-style logging.
People / Instructors | Flight Time Limitation (FTL) / duty tracking | Yes | Partial | Duty Hours page: today / trailing-7-day hours vs each instructor's Max Daily Hours, over-limit badge. | DELIBERATELY non-regulatory. DGCA FTL CAR was researched and found scoped to commercial air-transport crew, not FTO instructors. Reclassify only if DGCA confirms otherwise.
Aircraft & Maintenance | Aircraft fleet & status tracking | Yes | Built | 9-model fleet, DB-driven Type/Model, ACTIVE/MAINTENANCE/GROUNDED, fuel tracking. | Matches.
Aircraft & Maintenance | Maintenance due tracking (hour/calendar) | Yes | Built | Phase 1: per-model templates, hobbs/calendar due computation, non-blocking Due panel, Set-Baseline / Log-Completion actions, CSV bulk import. | Matches.
Aircraft & Maintenance | Hard enforcement — block booking an overdue aircraft | Implied | Not Built | Due panel is a warning only. | Phase 2. Precondition now met (Phase 1 clean in production since 08-27). Needs two decisions: which items hard-block, and how a false-positive baseline is handled before auto-grounding.
Aircraft & Maintenance | Pilot-reported squawks / defect reporting | Yes | Built | 'Report a Defect' page for instructor/student roles; server forces every staff-only field null regardless of client input. IMT-<year>-NNN ticket numbering. | CLOSED since the 08-27 snapshot.
Aircraft & Maintenance | Maintenance ticket numbering | Not advertised | Built | Year-scoped RMT-<year>-NNN (staff) and IMT-<year>-NNN (squawk). | AHEAD.
Aircraft & Maintenance | Float time logging | Yes (NEW Jun 2026) | N/A | — | NEW FlightLogger feature, North-America float-equipped aircraft. Not applicable to this FTO. Listed for completeness only.
Safety | Structured Safety Management System | Yes (SMS pillar) | Built | 5x5 ICAO risk matrix, OPEN → RESOLVED → CLOSED lifecycle, corrective actions, INC-<year>-NNN numbering, auto-routing of technical categories to Maintenance, three-tier report/manage/resolve permissions. Live-tested end to end. | CLOSED since the 08-27 snapshot, where this was the P1 'a log, not a workflow' gap.
Safety | Audit trail | Yes | Partial | completedBy / reportedBy / status history on the records that matter; no system-wide audit log. | No general-purpose audit log across all tables.
Safety | Breath Analyser (BA) test register + reporting | Not advertised | Built | Full BA Register + Daily/Weekly/Monthly report with PDF export, narrowed write access (safety_officer + operations only). | AHEAD. DGCA/FTO-specific.
Compliance & Reporting | DGCA-format Maintenance Log | N/A (region-specific) | Built | Parts used, certifying AME name + licence, CRS reference, is_baseline exclusion of synthetic rows, per-aircraft date-ranged report with PDF + styled XLSX export. | AHEAD (region-specific). ⚠️ Still carries a DRAFT FORMAT warning — layout unverified against a real CAMO-approved register.
Compliance & Reporting | DGCA Incident Report (statutory fields) | N/A (region-specific) | Not Built | safety_incidents captures the workflow but not the statutory notification field set. | Researched, designed and PARKED by the user 2026-09-10. Legal basis established: G.S.R. 829(E), Rule 4(2), eleven notification items. Unblocked whenever it is picked up.
Compliance & Reporting | Digital sign-offs on lessons/exams | Yes | Partial | Role-gated, server-verified completion with completedBy recorded. | Functionally a sign-off and an audit trail; not an e-signature artifact.
Compliance & Reporting | Regulator-ready compliance report pack | Yes (EASA/FAA/CASA) | Built | DGCA Audit Pack (/dashboard/reports/audit-pack), shipped 2026-09-11: one PDF for a date range bundling every saved Daily Flying Report, the BA register rollup, and the Maintenance Log for each aircraft with completed work. FOUR generators, not five as this row previously said — the BA Register page exports CSV only and has no PDF generator; the pack uses the BA Report rollup, which covers the same data over a range. | CLOSED 2026-09-11. Days with no saved Daily Flying Report are listed on the cover rather than omitted, so a pack with holes says so. Student logbooks deliberately excluded (per-student; a month across 20 students runs to hundreds of pages) — still exported individually. Range capped at 92 days.
Compliance & Reporting | Customizable / user-built report templates | Yes | Not Built | Reports are fixed, purpose-built pages. | Adding a report type needs a code change.
Finance | Student account balance / prepaid hours | Yes (User Balance Module) | Not Built | — | THE ONLY P1 LEFT. Largest functional gap versus FlightLogger.
Finance | Invoicing | Yes | Not Built | — | No invoice generation anywhere.
Finance | Payment processing | Implied | Not Built | — | No payment collection.
Finance | Accounting integration (QuickBooks) | Yes | Not Built | — | Defer well past a basic ledger.
Finance | Business Insights / analytics | Yes | Not Built | Operational widgets only (fuel, NOTAM, maintenance due). | No fleet-utilisation, instructor-productivity or revenue dashboards. Revenue half gated on Billing.
Communication | Internal messaging / announcements | Yes | Not Built | — | No in-app messaging.
Communication | Document / content library | Yes | Not Built | — | A simple Documents tab under Admin Setup would cover most of the need.
Communication | Automated alerts (expiry, schedule) | Yes | Built | Cron-driven email alerts for medical/SPL/CPL expiry via Resend; NOTAM and maintenance-due alerts on the dashboard. | Matches for expiry-driven alerts. No push notifications or schedule-change alerts.
Technical / Platform | Web application | Yes | Built | Next.js 16 / React 19 / Supabase, responsive, SWR data layer. | Matches.
Technical / Platform | Dedicated mobile app / PWA | Yes (mobile access) | Partial | Responsive layout works on phones and tablets. | Installability (manifest, service worker, offline) not built.
Technical / Platform | Public API for integrations | Yes | Not Built | Internal Next.js API routes only. | No documented public API.
Technical / Platform | Single sign-on (SSO) | Yes | Not Built | NextAuth email/password. | No SAML/OAuth org login.
Technical / Platform | Multi-location / multi-campus | Yes | Not Built | Single-organization, single-base data model. | Touches most of the data model. Not needed unless the FTO opens a second base.
Technical / Platform | Customizable branding | Yes | Built | Org logo upload, school/location name, light and dark theme. | Matches at a basic level; no white-label domain.
Technical / Platform | Self-service student portal | Yes | Built | Students log in to /dashboard/student for their own progress, requirements and records. | Matches.

## Gaps & Priorities
Priority | Area | Gap | Why It Matters | Recommendation | Rough Effort
P1 | Finance | No billing / invoicing / student account balance | Every FTO needs to know what each student owes or has prepaid. Now the ONLY unresolved P1 — the other three closed between 08-31 and 09-10. | Student ledger table, manual credit/debit tied to flight records, balance badge on the student profile, simple invoice/receipt PDF. Defer payment gateway and QuickBooks. | Large
P2 | Reporting | No consolidated DGCA audit-pack export — CLOSED 2026-09-11 | An inspection wants one pack, not five separate pages. SHIPPED 2026-09-11 as the DGCA Audit Pack (/dashboard/reports/audit-pack) and verified live. | Done. Note for anyone reading the old wording: there are FOUR PDF generators, not five — the BA Register page has CSV export only. The pack uses the BA Report rollup instead. | Small — DONE
P2 | Aircraft & Maintenance | Maintenance Phase 2 (hard-block overdue aircraft) | An aircraft overdue on a mandatory item can still be booked and flown. | Precondition met. Decide which items hard-block vs warn, and how a false-positive baseline is handled before auto-grounding. is_baseline (09-09) removes one obstacle. | Small-Medium
P2 | Student & Training | No pace-vs-target progression monitoring | FlightLogger shipped this as its own module. FPM knows hours, dates and targets but never asks whether a student is ON PACE — only how far along they are. | A computed view: required pace from program target and enrolment date vs actual booked/flown pace, with an ahead/behind badge. No new data needed. | Medium
P2 | Reporting | No business insights / analytics | No single view of fleet utilisation or instructor productivity. | Admin-only Insights page with a handful of KPIs over existing Flight Records / Scheduled Flights data. Revenue half gated on Billing. | Medium
P2 | Student & Training | Ground School has no e-learning content | Attendance and exam results are tracked; no content or quizzes delivered in-app. | Scope with the user first — could be 'attach a PDF to a subject' or a full quiz engine. Do not start without that decision. | Small to Large
P2 | Student & Training | No structured CBTA | Grading is complete/incomplete plus notes. | Only build if DGCA or the FTO SOP actually requires competency rubrics. Confirm first. | Large
P3 | Compliance | DGCA Incident Report statutory fields | Legal basis is established and the design is done; only the build remains. | Extend safety_incidents with the eleven Rule 4(2) notification items plus classification/injury/damage. Parked by the user 2026-09-10. | Medium
P3 | Student & Training | No combined flight + ground syllabus | New FlightLogger feature. FPM keeps the two modules separate. | Low urgency. A unified progress view over data both modules already hold. | Medium
P3 | Scheduling | Student self-booking unconfirmed | Unclear whether students book their own slots or staff always book for them. | Ask the user. Five minutes, may create no work at all. | Small
P3 | Technical / Platform | No calendar sync, SSO, public API, native app, multi-base | Standard in mature competitors, but integration/scale features rather than daily-ops gaps for a single-base FTO. | Defer until real demand. Building speculatively would be over-engineering at this scale. | Large each
P3 | Communication | No internal messaging or document library | Team comms and SOP storage happen outside the app. | A simple Documents tab under Admin Setup would cover most of the need. | Small if scoped to upload/list

## Changed Since 2026-08-27
Feature | Was | Now | When / Note
Drag-and-drop calendar rescheduling | Not Built | Built | 2026-09-01
Structured Safety Management System | Not Built | Built | 2026-09-01 — was a P1
Pilot-reported squawks / defect reporting | Not Built | Built | 2026-09-01 — was a P1
Flight Time Limitation / duty tracking | Not Built | Partial | 2026-09-01 — was a P1, shipped as an explicitly non-regulatory visibility tool
DGCA-format Maintenance Log | Partial (draft template only) | Built | 2026-09-09
Maintenance ticket numbering | n/a | Built | 2026-09-03
PIC / PICUS hour tracking | n/a | Built | 2026-09-10 — new capability, not a FlightLogger parity item
Weather / NOTAM | Built (dead endpoint) | Built (SkyLink) | 2026-09-05 — the old aviationweather.gov NOTAM endpoint had been discontinued
Digital student logbook | Built | Built (+PIC) | 2026-09-10 — now reports solo and PIC separately
Room / resource booking | Not Built | Partial | Reclassified — simulators are bookable as aircraft
Audit trail | Not Built | Partial | Reclassified — per-record attribution exists, system-wide log does not
Mobile app | Not Built | Partial | Reclassified — responsive layout works; installability does not
Combined flight + ground syllabus | — | Not Built | NEW FlightLogger feature, Jun 2026
Student Progression module | — | Not Built | NEW FlightLogger feature, Nov 2025 add-on
Float time logging | — | N/A | NEW FlightLogger feature, Jun 2026 — not applicable to this FTO
Regulator-ready compliance report pack | Partial | Built | 2026-09-11 — DGCA Audit Pack. Was flagged here as the cheapest real win; it was.
Quick-reschedule stale OVERDUE state | Open bug | Fixed + verified | 2026-09-11 — SWR cache splice was not revalidating derived fields.
Student Progression / pace-vs-target | Not Built | Partial | 2026-09-11 — projection half shipped; plan half needs course duration + joined dates